## WEEK 1
DAILY SCRUM TEMPLATE
Team member | Question | Monday | Tuesday | Wednesday | Thursday | Friday
Pasupuleti Jaswanth | What did you do yesterday? | None. | Drafted initial requirements for COS-1. Started high-level architecture for COS-2. | Completed repository setup for COS-3. Made good progress on COS-2 architecture document. | Finalized COS-2. Started on COS-4 communication protocols. | Made good progress on COS-4. Identified potential datasets for COS-8.
| What are doing today? | Starting work on COS-1 (Project setup), outlining initial requirements doc. Begin research for COS-2 (Define architecture). | Continue refining architecture for COS-2. Start setting up repositories for COS-3. | Finalize architecture document for COS-2. Begin defining communication | Continue with COS-4. Start research for COS-8 (Dataset for task management). | Aim to complete the first draft of COS-4. Document initial findings for COS-8. Plan for COS-11 (Encryption methods) and COS-13 (Prompt format) next week.
| Is there anything blocking you? | None. | None | Need input from Krithin on Big Data interface for COS-2. | None | None, planning for week review.
Dhanush | What did you do yesterday? | N/A | Identified several potential data sources for COS-6. | Shortlisted 2-3 key datasets for COS-6. Started outlining criteria for CV model selection (COS-10). | Successfully accessed one dataset for COS-6, started initial data quality checks. Refined CV model selection criteria (COS-10). | Completed initial preprocessing for one dataset (COS-6). Evaluated two CV models (COS-10).
| What are doing today? | Starting research for COS-6 (Gather dataset for CV LLM). Initial exploration of sources. | Continue evaluating data sources for CV LLM (COS-6). Begin high-level research for COS-10 (Select CV model). | Begin downloading/accessing data for COS-6. Continue defining selection criteria for COS-10. | Continue data quality checks and preprocessing for COS-6. Start evaluating specific CV models against criteria for COS-10. | Document findings for COS-6 dataset. Draft comparison for CV models (COS-10).
| Is there anything blocking you? | Clarification needed on specific password complexity rules for US003. | Some datasets require access requests. | Download speeds for one dataset are slow. | None | None
Baladitya | What did you do yesterday? | N/A | Researched standard encryption algorithms relevant to Quantum Security Framework (COS-7). | Drafted initial proposal for encryption methods for COS-7. | Refined encryption methods document for COS-7. | Good progress on detailing encapsulation and signature requirements for COS-7.
| What are doing today? | Kicking off research for COS-7 (Define data encryption methods for CS LLM). | Deep dive into selected algorithms for COS-7, evaluating pros and cons. | Refine proposal for COS-7. Start looking into encapsulation and signature algorithms as part of this task. | Focus on encapsulation and digital signature aspects for COS-7. | Focus on encapsulation and digital signature aspects for COS-7.
| Is there anything blocking you? | None. | Minor issues with library integration, debugging them. | Need to sync with Pasupuleti on overall security protocols (related to COS-4). | none | None
Krithin Thota | What did you do yesterday? | N/A | Analyzed initial data types expected for COS-37 | Completed data categorization for COS-37. Started outlining options for Hadoop/Spark for COS-38. | Made recommendations for COS-38. Began evaluating storage solutions (HDFS, Kafka, cloud) for COS-40. | Good progress on COS-40 and COS-41.
| What are doing today? | Starting on COS-37 (Identify structured vs. unstructured data). Reviewing project | Continue categorizing data for COS-37. Begin research for COS-38 (Define distributed processing framework) | Deep dive into framework selection for COS-38. Start on COS-40 (Select storage solution). | Continue COS-40. Start drafting COS-41 (Data partitioning & indexing strategies). | Aim to finalize storage solution proposal (COS-40). Continue drafting partitioning strategy (COS-41). Look into COS-42 (Interface Big Data & Central LLM) for next week.
| Is there anything blocking you? | None. | Minor issues with library integration, debugging them. | Clarification needed on expected data volumes for COS-40. | None | None
None

## WEEK 2
DAILY SCRUM TEMPLATE
Team member | Question | Monday | Tuesday | Wednesday | Thursday | Friday
Pasupuleti Jaswanth | What did you do yesterday? | Reviewed week 1 progress. Finalized COS-4 (Communication protocols). | Progressed on COS-11. Drafted initial prompt formats for COS-13. | Significant progress on COS-13 prompt formats. Added to COS-14 documentation. | COS-13 finalized. COS-14 documentation ongoing. | COS-14 documentation near completion.
| What are doing today? | Start detailed work on COS-11 (Finalise encryption methods for task transmission), incorporating inputs from bl.en.u4aie22064. Begin outlining COS-13 (Finalise prompt format). | Continue refining prompt formats for COS-13. Start documentation for COS-14 (Project scope and workflows). | Aim to finalize COS-13. Continue expanding COS-14. Review COS-8 (Dataset for task management) findings. | Focus on completing COS-14 documentation. Begin implementation planning for Central LLM development (COS-23 in Sprint 2). | Final review and commit for COS-14. Wrap up any pending items for COS-11. Prepare for Sprint 2 planning
| Is there anything blocking you? | Waiting for final encryption algorithm choice from bl.en.u4aie22064 for COS-11. | None | None | None | None,
Dhanush | What did you do yesterday? | Completed initial analysis of CV datasets (COS-6). Finalized CV model comparison (COS-10). | COS-10 (Select CV model) completed. Started setting up dev environment for CV LLM (COS-15). | Resolved library issue. Basic structure for COS-15 coded. | Implemented data loading for COS-15. | Good progress on CV model prediction logic (COS-15).
| What are doing today? | Formally select and document the CV model for COS-10. Begin planning for COS-15 (Implement CV LLM - Sprint 2). | Continue with CV LLM development environment setup. Start coding the basic structure for COS-15. | Implement core data loading and preprocessing logic for COS-15 using data from COS-6. | Start implementing the core prediction logic of the selected CV model in COS-15. | Test initial prediction outputs for COS-15. Refine and document.
| Is there anything blocking you? | None. | Minor library compatibility issue for CV LLM. | None | None | Predictions need further accuracy tuning.
Baladitya | What did you do yesterday? | Finalized documentation for COS-7 (Encryption methods for CS LLM). | Outlined modules for CS LLM (COS-19). | Dev environment for COS-19 setup. Started encryption service. | Encryption service for COS-19 largely complete. | Progressed on message integrity for COS-19.
| What are doing today? | Start planning for COS-19 (Implement CS LLM - Sprint 2). Define modules needed. | Begin setting up development environment for COS-19. Start coding the core encryption/decryption service. | Continue developing encryption service for COS-19. Plan integration points for quantum encryption module (COS-20 - Sprint 2). | Start working on message integrity components (related to COS-21 - Sprint 2) within the CS LLM framework (COS-19). | Test initial encryption and integrity functions. Document current implementation of COS-19.
| Is there anything blocking you? | None. | None. | None. | none | None
Krithin Thota | What did you do yesterday? | Finalized recommendations for COS-38 (Distributed framework) and COS-40 (Storage solution). Drafted COS-41 (Partitioning). | Progressed on COS-42 interface definition. | Received prompt format. Made significant progress on COS-42. | COS-42 interface design completed. Detailed pipeline plan for COS-49. | Outlined COS-50.
| What are doing today? | Complete documentation for COS-41. Start detailed work on COS-42 (Interface Big Data & Central LLM). | Continue with COS-42. Pick up COS-49 (Implement data pipelines to Central LLM - Sprint 2) planning. | Aim to finalize COS-42. Continue planning for COS-49 data pipelines. | Begin outlining implementation for COS-50 (Predictive analytics module - Sprint 2). | Review all Big Data Sprint 1 tasks (COS-37, 38, 40, 41, 42). Prepare for Sprint 2 implementation.
| Is there anything blocking you? | Needs prompt format from jaswanth(COS-13) to finalize COS-42 interface. | none | none | None | None

## WEEK 3
DAILY SCRUM TEMPLATE
Team member | Question | Monday | Tuesday | Wednesday | Thursday | Friday
Pasupuleti Jaswanth | What did you do yesterday? | Sprint 2 planning. Reviewed Sprint 1 completed items. | Coded initial task intake for COS-23. | Defined Central LLM interface for COS-28. | API endpoint design for COS-29 complete. | API stubs for COS-29 implemented. Progress on COS-23.
| What are doing today? | Begin development for COS-23 (Central LLM Development). Define core logic for task intake. | Start on COS-28 (Real-time data flow from CS/CV to Central LLM), focusing on defining the Central LLM side of the interface. | Start working on COS-29 (Set up APIs for task assignment). Design API endpoints. | Begin implementation of API stubs for COS-29. Continue core logic for COS-23. | Test task assignment API stubs (COS-29). Refine Central LLM core logic (COS-23).
| Is there anything blocking you? | None. | Need interface specs from Dhanush (CV) and bl.en.u4aie22064 (CS). | None | None | Minor issues with API stub testing.
Dhanush | What did you do yesterday? | Sprint 2 planning. Reviewed COS-15 (CV LLM) current state. | Tuned parameters for COS-15, saw slight accuracy improvement. Outlined training plan for COS-16. | COS-15 accuracy now acceptable for initial integration. Data prep for COS-16 ongoing. | COS-16 initial training run completed, results look promising. Started logic for COS-17. | COS-16 model evaluated. COS-17 logic largely complete.
| What are doing today? | Continue refining and testing COS-15 (Implement CV LLM). Focus on improving model accuracy. Start planning COS-16 (Train object detection model). | Implement further tuning for COS-15. Begin data preparation for training COS-16. | Start training run for COS-16. Begin working on COS-17 (Implement thresholding for severity scoring). | Evaluate COS-16 model. Continue implementing COS-17 severity scoring. | Integrate COS-17 with CV LLM (COS-15). Plan for COS-18 (Convert detections to structured prompts) next.
| Is there anything blocking you? | Model accuracy for COS-15 still needs improvement. | Data augmentation for COS-16 is time-consuming. | COS-16 training will run overnight. | None | Predictions need further accuracy tuning.
Baladitya | What did you do yesterday? | Sprint 2 planning. Reviewed COS-19 (CS LLM) current state. | Made progress integrating library for COS-20. | Resolved debugging issues for COS-20. Started COS-21 implementation. | COS-21 message integrity verification implemented and tested. | Good progress on COS-22 prompt conversion logic.
| What are doing today? | Continue development on COS-19. Start implementation of COS-20 (Implement quantum encryption for secure message relay). | Continue with COS-20. Start work on COS-21 (Establish message integrity verification). | Focus on completing COS-21. Test message integrity. | Start working on COS-22 (Convert task updates into structured prompts for Central LLM). | Test COS-22 prompt generation. Ensure CS LLM (COS-19) modules (COS-20, COS-21, COS-22) are working together.
| Is there anything blocking you? | Integrating quantum encryption library for COS-20 is complex. | Debugging issues with quantum encryption module (COS-20). | None. | Needs final prompt format from Jaswanth (COS-13). | None
Krithin Thota | What did you do yesterday? | Sprint 2 planning. Reviewed Big Data tasks. | CV LLM data pipeline (COS-49) initial version implemented. | CS LLM pipeline (COS-49) drafted. Initial predictive model for COS-50 selected. | Resolved data format issues in COS-49 pipelines. Progress on COS-50. | COS-50 predictive analytics module core logic complete.
| What are doing today? | Begin implementation of COS-49 (Implement data pipelines to feed Central LLM). Focus on CV LLM data first. | Start on CS LLM data pipeline for COS-49. Begin development for COS-50 (Predictive analytics module). | Refine and test both pipelines for COS-49. Start implementing base logic for COS-50. | Focus on developing core features of predictive analytics module (COS-50). | Test COS-50 with sample data. Document COS-49 and COS-50.
| Is there anything blocking you? | None. | none | Pipeline testing showing some data format mismatches. | None | Predictive accuracy of COS-50 needs further data.

## WEEK 4
DAILY SCRUM TEMPLATE
Team member | Question | Monday | Tuesday | Wednesday | Thursday | Friday
Pasupuleti Jaswanth | What did you do yesterday? | Reviewed Week 3 progress. Tested COS-29 API stubs. | Progress on COS-24. Integrated basic CV prompt intake. | COS-24 multi-source prompt processing largely functional. Initial algorithm for COS-25 drafted. | COS-25 algorithm tested. Research for COS-26 ongoing. | Final testing of Central LLM features for Sprint 2 (COS-23, 24, 25, 28, 29). Prepare for Sprint 3 performance testing (COS-30).
| What are doing today? | Integrate task assignment APIs (COS-29) with Central LLM core logic (COS-23). Start implementing COS-24 (Multi-source prompt processing). | Integrate CS prompt intake for COS-24. Start on COS-25 (Develop task prioritization algorithm). | Refine and test COS-25 prioritization. Begin COS-26 (Implement reinforcement learning for task optimization) - research phase. | Start basic framework for COS-26. Focus on testing real-time data flow (COS-28) with other LLMs. | Test task assignment API stubs (COS-29). Refine Central LLM core logic (COS-23).
| Is there anything blocking you? | Requires prompt outputs from CV (Dhanush) and CS (bl.en.u4aie22064) LLMs for COS-24. | Ensuring smooth data flow for COS-28 (Real-time data flow). | None | Intermittent connectivity issues during COS-28 testing. | Minor issues with API stub testing.
Dhanush | What did you do yesterday? | Reviewed Week 3 progress. Integrated severity scoring (COS-17) with CV LLM (COS-15). | Implemented prompt generation logic for COS-18. | COS-18 prompts finalized and tested. CV LLM ready for integration. | Participated in COS-28 integration tests. | Test scenarios for COS-31 documented. Discussed COS-52 with Krithin.
| What are doing today? | Start working on COS-18 (Convert detections into structured prompts for Central LLM). | Test COS-18 prompt outputs. Ensure CV LLM (COS-15, 16, 17, 18) is ready for integration testing. | Assist with COS-28 (Real-time data flow) integration testing from CV side. Plan for COS-31 (Stress-test CV LLM - Sprint 3). | Prepare test scenarios for COS-31. Start working on COS-52 (Test Big Data streaming performance - Sprint 3) with Krithin. | Final review of all CV LLM components for Sprint 2. Prepare for Sprint 3 tasks.
| Is there anything blocking you? | Needs final Central LLM prompt specifications from Krithin. | Minor adjustments needed to prompt format based on Pasupuleti's feedback. | None | None | None.
Baladitya | What did you do yesterday? | Reviewed Week 3 progress. CS LLM (COS-19, 20, 21, 22) modules tested individually. | CS LLM internal integration successful. | Participated in COS-28 integration tests. Latency from COS-20 seems acceptable. | Documented test plan for COS-32. | CS LLM Sprint 2 features finalized and documented.
| What are doing today? | Begin integration testing of all CS LLM modules. Ensure COS-22 prompts are correct. | Assist with COS-28 (Real-time data flow) integration testing from CS side. | Plan for COS-32 (Evaluate CS LLM’s latency under encrypted messaging - Sprint 3). | Refine any aspects of CS LLM based on integration learnings. Ensure full readiness for Sprint 2 demo. | Final review of CS LLM components. Prepare for Sprint 3 performance testing.
| Is there anything blocking you? | None. | Ensuring quantum encryption (COS-20) doesn't introduce significant latency in COS-28. | None. | Needs final prompt format from Jaswanth (COS-13). | None
Krithin Thota | What did you do yesterday? | Reviewed Week 3 progress. Tested COS-49 pipelines and COS-50 predictive module. | Discussed COS-33 with Pasupuleti. Identified potential optimization areas. | Dashboard components for COS-43 outlined. | Kafka/Spark environment for COS-44 setup. Started initial stream processing logic. | Progress on COS-44 and COS-45.
| What are doing today? | Start on COS-33 (Optimize Central LLM’s decision-making loop - Sprint 3) - initial research on optimization points based on current Central LLM. | Start work on COS-43 (Real-Time task analytics - Sprint 3). Design dashboard components. | Begin implementation of COS-44 (Implement Kafka/Spark Streaming for CV anomaly - Sprint 3). | Continue with COS-44. Discuss COS-52 (Test Big Data streaming performance) with Dhanush. Start COS-45 (Build batch & streaming pipelines - Sprint 3). | Finalize plans for Sprint 3 Big Data tasks (COS-43, 44, 45, 46, 47, 48, 53, 54). Review any pending Sprint 2 items.
| Is there anything blocking you? | Needs insights from Pasupuleti on Central LLM's current decision logic. | none | Setting up local Kafka/Spark environment for COS-44. | None | None.