## PRODUCT BACKLOG
PRODUCT BACKLOG
User Story ID | User Story | Estimate (size) | Priority | Sprint | Task owner | Estimated effort
US001 | As a System Operator, I want to receive clear, prioritized alerts for critical events (e.g., high-risk space debris, severe weather, critical security breach) so that I can take immediate appropriate action. | Medium | 1 | COS Sprint 3 | Krithin Thota | 20
US002 | As a System Operator, I want to be able to drill down into the details of a specific detected anomaly (e.g., space debris) so that I can understand its characteristics and potential impact. | Medium | 1 | COS Sprint 3 | Dhanush D | 10
US003 | As a System Operator, I want to view a log of all tasks assigned by the Central LLM, along with their current status (e.g., pending, in-progress, completed, failed) so that I can track operational responses. | Small | 1 | COS Sprint 3 | Krithin Thota | 20
US004 | As a System Operator, I want to see the predicted path or impact area for detected space debris or weather anomalies on a map interface so that I can visually understand the potential risks. | Small | 1 | COS Sprint 3 | Dhanush D | 15
US005 | As a System Operator, I want to access historical data and trends for detected anomalies and system responses so that I can contribute to post-event analysis and reporting. | Medium | 1 | COS Sprint 3 | Dhanush D | 20
US006 | As a Security Operations Analyst, I want to be immediately notified of any detected security breaches or attempts, along with information about the nature of the threat and affected systems, so that I can initiate incident response procedures | Small | 2 | COS Sprint 3 | Pasupuleti Jaswanth-[BL.EN.U4AIE22046] | 20
US007 | As a System Operator, I want to see a real-time overview of all detected anomalies on a dashboard so that I can quickly assess the current operational status. | Small | 1 | COS Sprint 3 | Dhanush D | 15
US008 | As a System Integrator, I want to integrate real-time event triggers for Central LLM task updates so that the system can react dynamically to new information. | Medium | 1 | COS Sprint 3 | Krithin Thota | 10
US009 | As a UI/UX Developer, I want to define a real-time dashboard/UI for data monitoring (using React/D3.js for visualization) so that users can easily understand system status and trends. | Medium | 1 | COS Sprint 3 | Krithin Thota | 10
US0010 | As a Data Engineer, I want to optimize data aggregation, compression & retrieval speed for anomaly records so that analysis is efficient | Large | 1 | COS Sprint 3 | bl.en.u4aie22064 | 10
US0011 | As a Data Engineer, I want to build batch & streaming pipelines to store and process large volumes of sensor data so that comprehensive analytics can be performed. | Medium | 2 | COS Sprint 3 | bl.en.u4aie22064 | 10
US0012 | As a Data Engineer, I want to implement Kafka/Spark Streaming to process CV anomaly detection data in real-time so that insights are available promptly. | Large | 2 | COS Sprint 3 | bl.en.u4aie22064 | 10
US0013 | As a System Administrator, I want to set up logging & monitoring tools for post-deployment analysis so that system health and performance can be tracked. | Medium | 3 | COS Sprint 3 | Krithin Thota | 10
US0014 | As a System Administrator, I want to deploy a UI for real-time monitoring of detected anomalies & task assignments so that operators can oversee system activity. | Small | 4 | COS Sprint 3 | Krithin Thota | 10
US0015 | As a Developer, I want to optimize task allocation efficiency so that resources are utilized effectively. | Medium | 4 | COS Sprint 3 | bl.en.u4aie22064 | 10
US0016 | As a Developer, I want to implement feedback loops to refine model accuracy so that the system continuously improves. | Medium | 1 | COS Sprint 3 | Krithin Thota | 10
US0017 | As a QA Engineer, I want to test Big Data streaming performance under extreme loads so that the system's scalability and reliability are confirmed. | Medium | 2 | COS Sprint 3 | Pasupuleti Jaswanth-[BL.EN.U4AIE22046] | 10
US0018 | As a QA Engineer, I want to optimize the Central LLMâ€™s decision-making loop so that it can respond quickly and effectively. | Medium | 2 | COS Sprint 3 | Pasupuleti Jaswanth-[BL.EN.U4AIE22046] | 10
US0019 | As a QA Engineer, I want to evaluate the CS LLMs latency under encrypted messaging so that communication delays are within acceptable limits. | Large | 1 | COS Sprint 3 | Pasupuleti Jaswanth-[BL.EN.U4AIE22046] | 10
US0020 | As a QA Engineer, I want to stress-test the CV LLM on high-speed debris detection so that its performance under demanding conditions is verified. | Large | 2 | COS Sprint 3 | Pasupuleti Jaswanth-[BL.EN.U4AIE22046] | 10
US0021 | As a Data Scientist, I want to develop a predictive analytics module using historical anomaly trends so that the system can anticipate future events or needs. | Medium | 3 | COS Sprint 2 | bl.en.u4aie22064 | 10
US0022 | As a Data Engineer, I want to implement data pipelines to feed the Central LLM with processed insights from CV & CS LLMs so that the central decision-making is well-informed. | Medium | 3 | COS Sprint 2 | bl.en.u4aie22064 | 20
US0023 | As a System Integrator, I want to set up APIs for task assignment so that the Central LLM can delegate tasks to appropriate sub-LLMs or actors. | Medium | 4 | COS Sprint 2 | Pasupuleti Jaswanth-[BL.EN.U4AIE22046] | 20
US0024 | As a System Integrator, I want to establish real-time data flow from CS LLM & CV LLM to the Central LLM so that the central system has up-to-date information. | Medium | 2 | COS Sprint 2 | Pasupuleti Jaswanth-[BL.EN.U4AIE22046] | 10
US0025 | As an LLM Developer, I want to implement reinforcement learning for task optimization so that the system can improve its decision-making over time. | Medium | 2 | COS Sprint 2 | Krithin Thota | 20
US0026 | As an LLM Developer, I want to develop a task prioritization algorithm based on severity and urgency so that critical tasks are addressed promptly. | Medium | 3 | COS Sprint 2 | Krithin Thota | 20
US0027 | As an LLM Developer, I want to implement multi-source prompt processing so that the Central LLM can integrate information from various sub-LLMs. | Large | 3 | COS Sprint 2 | Krithin Thota | 20
US0028 | As an LLM Developer, I want to convert task updates into structured prompts for the Central LLM so that the central system is aware of security-related information. | Medium | 1 | COS Sprint 2 | Krithin Thota | 20
US0029 | As a Security Specialist, I want to establish message integrity verification so that data tampering can be detected. | Medium | 2 | COS Sprint 2 | Pasupuleti Jaswanth-[BL.EN.U4AIE22046] | 10
US0030 | As a Security Specialist, I want to implement quantum encryption for secure message relay so that inter-LLM communication is protected. | Small | 4 | COS Sprint 2 | Pasupuleti Jaswanth-[BL.EN.U4AIE22046] | 20
US0031 | As a CV Developer, I want to convert detections into structured prompts for the Central LLM so that information can be passed for further processing. | Large | 5 | COS Sprint 2 | Dhanush D | 10
US0029 | As a CV Developer, I want to implement thresholding for severity scoring so that the urgency of detected events can be assessed. | Medium | 3 | COS Sprint 2 | Dhanush D | 20
US0030 | As a CV Developer, I want to train an object detection model for debris and weather anomalies so that the system can identify relevant events. | Medium | 3 | COS Sprint 2 | Dhanush D | 20
US0031 | As a Data Architect, I want to establish data partitioning and indexing strategies so that data retrieval and processing are optimized. | Medium | 3 | COS Sprint 1 | bl.en.u4aie22064 | 10
US0032 | As a Data Architect, I want to select a suitable storage solution (HDFS, Apache Kafka, or cloud-based) so that all node and model data is stored efficiently and scalably. | Medium | 3 | COS Sprint 1 | bl.en.u4aie22064 | 10
US0033 | As a Data Architect, I want to define the interface between Big Data systems and the Central LLM so that data can be effectively utilized for decision-making | Medium | 3 | COS Sprint 1 | bl.en.u4aie22064 | 20
US0034 | As a Project Manager, I want to document the project scope and workflows so that all team members have a clear understanding of objectives and processes. | Medium | 3 | COS Sprint 1 | Pasupuleti Jaswanth-[BL.EN.U4AIE22046] | 10
US0035 | As an LLM Developer, I want to finalize the prompt format for the central LLM so that there's a standardized way for LLM nodes to exchange information. | Medium | 3 | COS Sprint 1 | Krithin Thota | 20
US0036 | As a Security Specialist, I want to finalize and apply encryption methods for secure task transmission so that data integrity and confidentiality are maintained. | Medium | 3 | COS Sprint 1 | Pasupuleti Jaswanth-[BL.EN.U4AIE22046] | 20
US0037 | As a CV Developer, I want to select the CV model for weather prediction and asteroid detection so that implementation can begin. | Medium | 3 | COS Sprint 1 | Dhanush D | 20
US0038 | As a Project Team Member, I want to research and define models for different project domains so that we select the most suitable algorithms. | Medium | 3 | COS Sprint 1 | Dhanush D | 10
US0039 | As a Data Architect, I want to define a distributed processing framework (Hadoop/Spark) for real-time data flow so that large volumes of data can be handled efficiently. | Medium | 3 | COS Sprint 1 | bl.en.u4aie22064 | 10
US0040 | As a Data Engineer, I want to identify structured vs. unstructured data for Big Data processing so that appropriate tools and techniques can be applied. | Medium | 3 | COS Sprint 1 | bl.en.u4aie22064 | 10
US0041 | As an LLM Developer, I want to gather datasets for task management to train the LLMs (sub and central nodes) so that they can effectively assign and manage tasks. | Medium | 3 | COS Sprint 1 | Krithin Thota | 30
US0042 | As a Security Specialist, I want to define data encryption methods for the CS LLM (Quantum Security Framework) so that communication between LLM nodes is secure. | Medium | 3 | COS Sprint 1 | Pasupuleti Jaswanth-[BL.EN.U4AIE22046] | 10
US0043 | As a CV Developer, I want to gather datasets for the CV LLM (space debris, weather anomalies) so that it can be trained for accurate detection. | Medium | 3 | COS Sprint 1 | Dhanush D | 10
US0044 | As a Data Scientist, I want to gather appropriate datasets for all project domains so that models can be trained effectively. | Medium | 3 | COS Sprint 1 | bl.en.u4aie22064 | 30
US0045 | As a Project Team Member, I want communication protocols to be defined so that LLMs and domains can interact seamlessly. | Medium | 3 | COS Sprint 1 | Pasupuleti Jaswanth-[BL.EN.U4AIE22046] | 10
US0046 | As a Developer, I want the project repositories to be set up so that code can be version controlled and easily accessed by the team. | Medium | 3 | COS Sprint 1 | Pasupuleti Jaswanth-[BL.EN.U4AIE22046] | 10
US0047 | As a System Architect, I want to define the architecture for CS LLM, CV LLM, and Central LLM so that there is a common understanding and communication framework for the different components. | Medium | 3 | COS Sprint 1 | Krithin Thota | 10
US0048 | As a Project Team Member, I want the initial project requirements to be set up so that we have a clear foundation to start working. | Medium | 3 | COS Sprint 1 | Pasupuleti Jaswanth-[BL.EN.U4AIE22046] | 10
Note on D8: stakeholdermap.com: Whatever method you are using for estimation. It could be story points, Fibonacci scale or T-shirt sizes - small, medium, large.
Note on E8: stakeholdermap.com: To change the Priority menu click on the DROPDOWN MENUS worksheet.
Note on F8: stakeholdermap.com: To change the Priority menu click on the DROPDOWN MENUS worksheet.
Note on G8: stakeholdermap.com: An optional field for the person responsible for the completion of the User Story.
Note on H8: stakeholdermap.com: This is an optional field for estimated effort in hours or days.

## PROJECT DETAILS
PROJECT NUMBER
PROJECT NAME | Coordinated orbital systems management and operations suite
PROJECT MANAGER
DATE
VERSION | 1

## DROPDOWN MENUS
PRIORITY | SPRINT
1 | 1
2 | 2
3 | 3
4 | 4
5 | 5
6
7
8
9
10
TO EDIT THE DROPDOWN MENUS
Click on the Data tab. Under Data Tools, select Data Validation. Under Settings change the Source to match the values you want to appear in the menu.
TO DELETE THE DROPDOWN MENUS
Click on the Data tab. Under Data Tools, select Data Validation. Under Settings change the Allow to Any value.

## RESOURCES
Useful resources
Burndown Chart Template
Daily Scrum Meeting Template
Project Management Templates
The Top 50 Business Risks (and how to manage them)!
Issue Log Template [free download]
End Project Report Template
Risk Register Template
Stakeholder Management Templates
Work Breakdown Structure (WBS) template in Excel